## AI Engineer 30-Day Plan
Date | Day | Track | Focus | Topics | Daily Deliverable | Target Hours | Actual Hours | Status | Confidence 1-5 | What I Built/Learned | Weak Areas | Interview Questions | Revision Needed?
2026-10-06 | Day 1 | LEARNING | LLM Foundations | tokens, embeddings, inference, temperature, top-p, context windows | Explain the LLM inference pipeline; run 3 decoding experiments | 2.5 |  | Not Started
2026-10-07 | Day 2 | LEARNING | Transformer Architecture | tokenization, embeddings, Q/K/V, self-attention, multi-head attention, causal masking | Whiteboard a decoder-only Transformer and explain attention | 3 |  | Not Started
2026-10-08 | Day 3 | LEARNING | LLM APIs + Structured Output | model APIs, system prompts, JSON/schema output, streaming, token/cost basics | Build a small structured-output LLM service | 2.5 |  | Not Started
2026-10-09 | Day 4 | LEARNING | Embeddings | embedding models, cosine/dot product, dimensions, semantic similarity | Compare 2 embedding approaches on a small dataset | 2.5 |  | Not Started
2026-10-10 | Day 5 | LEARNING | Vector Databases | ANN, HNSW, metadata filtering, indexing, pgvector/Qdrant concepts | Build basic vector search with metadata filters | 3 |  | Not Started
2026-10-11 | Day 6 | LEARNING | PROJECT — Week 1 | Project architecture + ingestion foundation | Weekend: choose corpus, repo structure, ingestion pipeline, initial README + architecture diagram | 3 |  | Not Started
2026-10-12 | Day 7 | LEARNING | PROJECT — Week 1 | RAG baseline | Weekend: complete baseline RAG end-to-end and document design decisions | 3 |  | Not Started
2026-10-13 | Day 8 | LEARNING | RAG Retrieval | dense vs sparse, BM25, hybrid retrieval, top-k, filters | Implement and compare dense vs keyword vs hybrid retrieval | 3 |  | Not Started
2026-10-14 | Day 9 | LEARNING | Chunking Strategies | fixed, recursive, semantic, document-aware, overlap, parent-child | Run a chunking experiment and record retrieval differences | 3 |  | Not Started
2026-10-15 | Day 10 | LEARNING | Reranking + Query Transformation | cross-encoder reranking, query rewriting, multi-query, HyDE concept | Add reranking/query transformation and measure impact | 3 |  | Not Started
2026-10-16 | Day 11 | LEARNING | RAG Evaluation | Recall@K, Precision@K, MRR, NDCG, relevance, faithfulness, groundedness | Create 20–30 evaluation questions and baseline metrics | 3 |  | Not Started
2026-10-17 | Day 12 | LEARNING | Context Engineering | context selection, compression, history, summarization, lost-in-the-middle | Implement context selection/compression strategy | 3 |  | Not Started
2026-10-18 | Day 13 | LEARNING | PROJECT — Week 2 | Advanced RAG | Weekend: integrate best retrieval strategy + reranking + evaluation into project | 3 |  | Not Started
2026-10-19 | Day 14 | LEARNING | PROJECT — Week 2 | RAG quality iteration | Weekend: analyze failures, tune chunks/retrieval/context, update evaluation report | 3 |  | Not Started
2026-10-20 | Day 15 | LEARNING | Tool Calling | tool schemas, function calling, validation, tool execution loop | Build 2–3 safe tools with validation and error handling | 3 |  | Not Started
2026-10-21 | Day 16 | LEARNING | Agents vs Workflows | agent loop, deterministic workflows, routing, state, when not to use agents | Implement a router/workflow and explain why/when an agent is justified | 3 |  | Not Started
2026-10-22 | Day 17 | LEARNING | LangGraph | state, nodes, edges, conditional routing, cycles, persistence | Build a stateful LangGraph workflow | 3 |  | Not Started
2026-10-23 | Day 18 | LEARNING | Agent Reliability | timeouts, retries, max iterations, fallback, graceful degradation | Add reliability controls to your agent | 3 |  | Not Started
2026-10-24 | Day 19 | LEARNING | MCP | MCP architecture, tools/resources/prompts, client/server, MCP vs APIs | Build one small MCP integration or a documented prototype | 2.5 |  | Not Started
2026-10-25 | Day 20 | LEARNING | PROJECT — Week 3 | Agent/tool layer | Weekend: add one agentic capability to project only where it adds real value | 3 |  | Not Started
2026-10-26 | Day 21 | LEARNING | PROJECT — Week 3 | Reliability + decision log | Weekend: add fallback/retry/guardrails; document architectural tradeoffs | 3 |  | Not Started
2026-10-27 | Day 22 | LEARNING | LLM Selection + Local Models | quality/latency/cost/privacy, model routing, quantization, VRAM, local inference | Create a model-selection matrix and test at least one local model | 3 |  | Not Started
2026-10-28 | Day 23 | LEARNING | Fine-Tuning | RAG vs prompting vs fine-tuning, SFT, LoRA, QLoRA, DPO concepts | Run or reproduce a small LoRA/QLoRA experiment; write a decision guide | 3 |  | Not Started
2026-10-29 | Day 24 | LEARNING | Evaluation + Observability | golden datasets, LLM-as-judge, tracing, latency, token usage, cost, regression | Add tracing/evaluation and create a regression test set | 3 |  | Not Started
2026-10-30 | Day 25 | LEARNING | AI Security | prompt injection, indirect injection, data leakage, tool abuse, permissions, RAG poisoning | Threat-model project and implement 3 mitigations | 3 |  | Not Started
2026-10-31 | Day 26 | LEARNING | PROJECT — Week 4 | Production hardening | Weekend: observability, security, evals, model configuration, error handling | 3 |  | Not Started
2026-11-01 | Day 27 | LEARNING | PROJECT — Week 4 | Project polish | Weekend: clean README, architecture diagram, demo flow, benchmark/evaluation results | 3 |  | Not Started
2026-11-02 | Day 28 | LEARNING | AI System Design | RAG/agent architecture, scalability, latency, cost, reliability, tradeoffs | Design a production AI system from requirements and defend decisions | 3 |  | Not Started
2026-11-03 | Day 29 | LEARNING | Interview Deep Dive | Transformer, RAG, agents, evaluation, fine-tuning, model selection | Timed drill: 30 technical questions + 2 system-design questions | 3 |  | Not Started
2026-11-04 | Day 30 | LEARNING | Final Project Defense | architecture, tradeoffs, failures, metrics, future improvements | Present project as an interview case study; identify next 30-day gaps | 3 |  | Not Started

## Dashboard
AI Engineer — 30-Day Working-Professional Plan
Start Date | 2026-10-06
End Date | 2026-11-04
Days Completed
Completion %
Target Hours
Actual Hours
Average Confidence
Project Days
Weekly Review
Week | Learning Focus | Project Output | Completed Days | Actual Hours | Avg Confidence
Week 1 | LLM + Transformers + Embeddings | Baseline RAG
Week 2 | RAG retrieval + evaluation + context | Advanced RAG
Week 3 | Tools + Agents + LangGraph + MCP | Agent/tool capability
Week 4 | Models + Fine-tuning + Eval + Security | Production hardening

## Project Selection
Project Selection — choose ONE primary project
Project Idea | What it demonstrates | AI Concepts | Backend/Engineering | Risk | Why it is interview-worthy
Engineering Knowledge & Incident Copilot | Turns internal-style docs, runbooks, API docs and incident reports into a grounded assistant that can retrieve evidence, diagnose issues and optionally call safe tools. | RAG, hybrid retrieval, reranking, context engineering, agents, tool calling, evals, guardrails, model selection | FastAPI, PostgreSQL/pgvector, Redis, async jobs, auth concepts, observability, Docker | Medium | Strongest overall fit: lets you show retrieval decisions, agent boundaries, evaluation, reliability and backend thinking without being a generic chatbot.
AI Research / Technical Literature Assistant | Ingests technical papers/docs, compares sources, creates evidence-backed summaries and answers questions with citations. | RAG, chunking, reranking, query decomposition, citations, context management, evaluation | Document ingestion, metadata, caching, APIs, background processing, observability | Medium | Excellent for demonstrating RAG depth and evaluation; less opportunity to show complex tool orchestration.
Data Analyst Agent with SQL + Knowledge RAG | Answers business questions by combining structured SQL data with unstructured documentation, choosing the correct source and citing evidence. | SQL agent, RAG, routing, tool calling, structured output, evaluation, guardrails | PostgreSQL, query validation, permissions, caching, async jobs, APIs | Medium-High | Very strong AI Engineer story because it forces routing, tool safety and source selection; also showcases backend experience.
AI Support Resolution Agent | Classifies a support issue, retrieves policy/product evidence, proposes a response and uses controlled tools for actions. | RAG, agents, routing, tool calling, memory/context, evaluation, guardrails | API design, state, queues, retries, audit logs, observability | Medium-High | Shows real-world agent design and reliability; avoid making it a simple FAQ bot.

## Rules
Rules for the 30-day plan
1. This plan assumes ~3 hours/day and a working professional schedule.
2. Backend fundamentals are intentionally compressed because you already have backend experience.
3. Do not chase every framework. Learn the underlying concept first, then implement it with one framework.
4. Every learning day ends with a concrete deliverable.
5. Every weekend is project time: integrate that week's strongest concepts into the same project.
6. Keep an architecture decision log: decision → alternatives → why chosen → tradeoff.
7. Keep an evaluation log: baseline → change → metric → result → conclusion.
8. For interview readiness, you must be able to explain why a design is appropriate, not just how the library works.
9. AI Backend topics such as deep distributed systems, Kubernetes and advanced cloud deployment are deliberately deferred until the AI Engineer foundation is solid.
10. By Day 30 the project should be your main interview artifact.